## Summary
FactoryGrid delivery tracker
Two developers in parallel: one backend, one frontend. Built from the FactoryGrid Backend Plan and Frontend Plan (10 Oct 2026). Master plan: FactoryGrid Development Plan (Node.js).
How to use: update the yellow Status cells on Tasks, Hand-offs and Open questions. Everything on this sheet recalculates.
Key dates |  | Days left
Development starts | 2026-10-12 | 2
Code freeze | 2027-01-14 | 96
Beta opens | 2027-01-15 | 97
Go/no-go | 2027-01-27 | 109
Production go-live | 2027-01-28 | 110
Final delivery | 2027-01-30 | 112
Progress
Owner | Total tasks | Done | In progress | Blocked | Not started | % done | Overdue (not done, past due)
Backend | 59 | 0 | 0 | 0 | 59 | 0% | 0
Frontend | 57 | 0 | 0 | 0 | 57 | 0% | 0
Total | 116 | 0 | 0 | 0 | 116 | 0% | 0
Progress by phase
Phase | Start | End | Backend % done | Frontend % done | Exit gates passed
Phase 0 / F0: Foundations | 2026-10-12 | 2026-10-16 | 0% | 0% | 0 of 2
Phase 1 / F1: Identity | 2026-10-19 | 2026-10-30 | 0% | 0% | 0 of 2
Phase 2 / F2: Partners, files, compliance | 2026-11-02 | 2026-11-20 | 0% | 0% | 0 of 2
Phase 3 / F3: Catalog and pricing | 2026-11-23 | 2026-12-04 | 0% | 0% | 0 of 2
Phase 4 / F4: Sourcing | 2026-12-07 | 2026-12-18 | 0% | 0% | 0 of 2
Phase 5 / F5: Orders and payments | 2026-12-21 | 2027-01-05 | 0% | 0% | 0 of 2
Phase 6 / F6: Logistics, notifications, dashboards | 2027-01-06 | 2027-01-12 | 0% | 0% | 0 of 2
Hardening and code freeze | 2027-01-12 | 2027-01-14 | 0% | 0% | 0 of 0
Beta testing and launch | 2027-01-15 | 2027-01-30 | 0% | 0% | 0 of 0
Formulas:
Overdue (not done, past due) = COUNTIFS(Tasks!$C2:C117,[Owner],Tasks!$H2:H117,"<>Done",Tasks!$G2:G117,"<"&TODAY())

## Tasks
ID | Phase | Owner | Type | Task | Start | Due | Status | Notes
BE-001 | Phase 0 / F0: Foundations | Backend | Task | pnpm workspace + Nx; backend/apps/factorygrid-api, libs/ for auth, errors, prisma, outbox, testing | 2026-10-12 | 2026-10-16 | Not started
BE-002 | Phase 0 / F0: Foundations | Backend | Task | API standards doc: /api/v1, ApiResponse / ErrorResponse, paging, Idempotency-Key, UTC dates, money in paise | 2026-10-12 | 2026-10-16 | Not started
BE-003 | Phase 0 / F0: Foundations | Backend | Task | docker-compose: PostgreSQL 17, Redis, MinIO, Mailpit | 2026-10-12 | 2026-10-16 | Not started
BE-004 | Phase 0 / F0: Foundations | Backend | Task | GitHub Actions: lint, type-check, Jest, OpenAPI lint, contract test, Docker image | 2026-10-12 | 2026-10-16 | Not started
BE-005 | Phase 0 / F0: Foundations | Backend | Task | Staging environment with database, Redis, S3 bucket and auto-deploy from main | 2026-10-12 | 2026-10-16 | Not started
BE-006 | Phase 0 / F0: Foundations | Backend | Task | pino logs with request ID, health endpoint, Swagger at /docs | 2026-10-12 | 2026-10-16 | Not started
BE-007 | Phase 0 / F0: Foundations | Backend | Hand-off | Write and freeze the Identity contract | 2026-10-12 | 2026-10-14 | Not started
BE-008 | Phase 0 / F0: Foundations | Backend | Task | Apply for Razorpay live KYC, GST/PAN provider account and email provider (SES or SendGrid) | 2026-10-12 | 2026-10-16 | Not started
BE-009 | Phase 0 / F0: Foundations | Backend | Exit gate | hello-world module deploys to staging behind JWT auth from CI | 2026-10-12 | 2026-10-16 | Not started
FE-010 | Phase 0 / F0: Foundations | Frontend | Task | Remove VITE_RAZORPAY_KEY_SECRET and verifyRazorpaySignature from razorpayService.ts, and every provider key from VITE_ variables | 2026-10-12 | 2026-10-12 | Not started
FE-011 | Phase 0 / F0: Foundations | Frontend | Task | Move frontend/ into the pnpm workspace; import @factorygrid/contracts | 2026-10-12 | 2026-10-16 | Not started
FE-012 | Phase 0 / F0: Foundations | Frontend | Task | One HTTP layer on openapi-fetch: VITE_API_BASE_URL, bearer token, refresh on 401, request ID header, error toasts from ErrorResponse | 2026-10-12 | 2026-10-16 | Not started
FE-013 | Phase 0 / F0: Foundations | Frontend | Task | TanStack Query set up with standard loading, error and retry behaviour | 2026-10-12 | 2026-10-16 | Not started
FE-014 | Phase 0 / F0: Foundations | Frontend | Task | MSW with a per-module mock/live switch | 2026-10-12 | 2026-10-16 | Not started
FE-015 | Phase 0 / F0: Foundations | Frontend | Task | Route guards by role from /me; remove hard-coded role switching | 2026-10-12 | 2026-10-16 | Not started
FE-016 | Phase 0 / F0: Foundations | Frontend | Task | Vitest + Testing Library, Playwright, and both in CI | 2026-10-12 | 2026-10-16 | Not started
FE-017 | Phase 0 / F0: Foundations | Frontend | Task | Update vercel.json for the workspace (pnpm install --frozen-lockfile, pnpm --filter frontend build) | 2026-10-12 | 2026-10-16 | Not started
FE-018 | Phase 0 / F0: Foundations | Frontend | Hand-off | Review the Identity contract; start login screens on mocks | 2026-10-12 | 2026-10-14 | Not started
FE-019 | Phase 0 / F0: Foundations | Frontend | Exit gate | app builds from the workspace on Vercel, logs in against the Identity mock, no secret in bundle | 2026-10-12 | 2026-10-16 | Not started
BE-020 | Phase 1 / F1: Identity | Backend | Task | prisma db pull on the existing IAM schema and baseline it; keep tables and BCrypt hashes | 2026-10-19 | 2026-10-30 | Not started
BE-021 | Phase 1 / F1: Identity | Backend | Task | Port login, refresh, logout, me, register/buyer, register/manufacturer with the same JSON shapes | 2026-10-19 | 2026-10-30 | Not started
BE-022 | Phase 1 / F1: Identity | Backend | Task | Rewrite IamSecurityAndAuthTest and UserRepositoryTest as Jest + Supertest; all pass | 2026-10-19 | 2026-10-30 | Not started
BE-023 | Phase 1 / F1: Identity | Backend | Task | Link users to organizations; user admin APIs (invite, deactivate, assign roles) | 2026-10-19 | 2026-10-30 | Not started
BE-024 | Phase 1 / F1: Identity | Backend | Task | Role guard on every endpoint, with a 403 test per role | 2026-10-19 | 2026-10-30 | Not started
BE-025 | Phase 1 / F1: Identity | Backend | Task | TOTP 2FA server-side (move totpUtils.ts logic), password reset, email verification, login audit | 2026-10-19 | 2026-10-30 | Not started
BE-026 | Phase 1 / F1: Identity | Backend | Task | Notification module v1: transactional email with templates, sent as BullMQ jobs | 2026-10-19 | 2026-10-30 | Not started
BE-027 | Phase 1 / F1: Identity | Backend | Hand-off | Write and freeze the Partners/files/compliance contract | 2026-10-19 | 2026-10-28 | Not started
BE-028 | Phase 1 / F1: Identity | Backend | Exit gate | all 8 roles register or are invited, verify email, log in with 2FA, reset password; existing users keep passwords; Java IAM retired | 2026-10-19 | 2026-10-30 | Not started
FE-029 | Phase 1 / F1: Identity | Frontend | Task | LoginPage, Security2FA, BuyerSecuritySettings, Settings, password reset, email verification, invite acceptance | 2026-10-19 | 2026-10-30 | Not started
FE-030 | Phase 1 / F1: Identity | Frontend | Task | User admin screens: invite, deactivate, assign roles | 2026-10-19 | 2026-10-30 | Not started
FE-031 | Phase 1 / F1: Identity | Frontend | Task | Remove the auth slice from AppContext | 2026-10-19 | 2026-10-30 | Not started
FE-032 | Phase 1 / F1: Identity | Frontend | Task | Shared building blocks: server-paged data table, form field errors from the API, presigned file upload, empty/error/loading states | 2026-10-19 | 2026-10-30 | Not started
FE-033 | Phase 1 / F1: Identity | Frontend | Hand-off | Review the Partners/files/compliance contract | 2026-10-19 | 2026-10-28 | Not started
FE-034 | Phase 1 / F1: Identity | Frontend | Exit gate | login, 2FA, reset and invite work against the Node.js IAM on staging for all 8 roles | 2026-10-19 | 2026-10-30 | Not started
BE-035 | Phase 2 / F2: Partners, files, compliance | Backend | Task | Partner module: organizations, onboarding drafts per wizard step, profiles, capabilities, facilities, certifications, customer segments | 2026-11-02 | 2026-11-20 | Not started
BE-036 | Phase 2 / F2: Partners, files, compliance | Backend | Task | File module: presigned S3 uploads, document versions, expiry dates | 2026-11-02 | 2026-11-20 | Not started
BE-037 | Phase 2 / F2: Partners, files, compliance | Backend | Task | Compliance module: verification cases, GST/PAN check via one provider adapter with a fake, admin approval queue, audit log | 2026-11-02 | 2026-11-20 | Not started
BE-038 | Phase 2 / F2: Partners, files, compliance | Backend | Task | Move GST connector logic from the frontend to the backend adapter; keys server-side only | 2026-11-02 | 2026-11-20 | Not started
BE-039 | Phase 2 / F2: Partners, files, compliance | Backend | Hand-off | Write and freeze the Catalog/pricing contract | 2026-11-02 | 2026-11-18 | Not started
BE-040 | Phase 2 / F2: Partners, files, compliance | Backend | Exit gate | buyer and manufacturer onboard, upload documents, approved or rejected by admin, every step audited | 2026-11-02 | 2026-11-20 | Not started
FE-041 | Phase 2 / F2: Partners, files, compliance | Frontend | Task | Buyer and Manufacturer onboarding wizards, saving each step as a draft | 2026-11-02 | 2026-11-20 | Not started
FE-042 | Phase 2 / F2: Partners, files, compliance | Frontend | Task | Profile, ManufacturerProfilePage, Customer, CustomerSegmentMaster | 2026-11-02 | 2026-11-20 | Not started
FE-043 | Phase 2 / F2: Partners, files, compliance | Frontend | Task | CustomerVerification, ManufacturerVerification, Brand and Trademark verification | 2026-11-02 | 2026-11-20 | Not started
FE-044 | Phase 2 / F2: Partners, files, compliance | Frontend | Task | All Admin*Verification screens and monitors, AdminApproval, Compliance (audit log view) | 2026-11-02 | 2026-11-20 | Not started
FE-045 | Phase 2 / F2: Partners, files, compliance | Frontend | Task | Delete partner and compliance mock data | 2026-11-02 | 2026-11-20 | Not started
FE-046 | Phase 2 / F2: Partners, files, compliance | Frontend | Hand-off | Review the Catalog/pricing contract | 2026-11-02 | 2026-11-18 | Not started
FE-047 | Phase 2 / F2: Partners, files, compliance | Frontend | Exit gate | buyer and manufacturer onboard with real uploads; admin approves or rejects | 2026-11-02 | 2026-11-20 | Not started
BE-048 | Phase 3 / F3: Catalog and pricing | Backend | Task | Catalog module: products, 3-level categories, brands, attributes, UoM, tax rules, product-manufacturer mapping | 2026-11-23 | 2026-12-04 | Not started
BE-049 | Phase 3 / F3: Catalog and pricing | Backend | Task | CSV/Excel bulk import as a BullMQ job with an error report | 2026-11-23 | 2026-12-04 | Not started
BE-050 | Phase 3 / F3: Catalog and pricing | Backend | Task | Server-side search, filters and paging on product lists | 2026-11-23 | 2026-12-04 | Not started
BE-051 | Phase 3 / F3: Catalog and pricing | Backend | Task | Pricing module: price lists by segment, margin rules by scope, platform fees, price calculation API; integer paise and decimal.js only | 2026-11-23 | 2026-12-04 | Not started
BE-052 | Phase 3 / F3: Catalog and pricing | Backend | Task | Rounding unit tests on every price rule | 2026-11-23 | 2026-12-04 | Not started
BE-053 | Phase 3 / F3: Catalog and pricing | Backend | Hand-off | Write and freeze the Sourcing contract | 2026-11-23 | 2026-12-02 | Not started
BE-054 | Phase 3 / F3: Catalog and pricing | Backend | Exit gate | buyers search a catalog with live prices matching their segment's margin rules | 2026-11-23 | 2026-12-04 | Not started
FE-055 | Phase 3 / F3: Catalog and pricing | Frontend | Task | ProductCatalog, CategoryMaster, BrandMaster, AttributeMaster, ProductUom, ProductTax, ProductManufacturerMapping | 2026-11-23 | 2026-12-04 | Not started
FE-056 | Phase 3 / F3: Catalog and pricing | Frontend | Task | ProductPrice, MarginEngine; Buyer and Manufacturer product catalogs | 2026-11-23 | 2026-12-04 | Not started
FE-057 | Phase 3 / F3: Catalog and pricing | Frontend | Task | CSV/Excel import screen with job progress and error report download | 2026-11-23 | 2026-12-04 | Not started
FE-058 | Phase 3 / F3: Catalog and pricing | Frontend | Task | Server-side search, filter and paging on every catalog list | 2026-11-23 | 2026-12-04 | Not started
FE-059 | Phase 3 / F3: Catalog and pricing | Frontend | Hand-off | Review the Sourcing contract | 2026-11-23 | 2026-12-02 | Not started
FE-060 | Phase 3 / F3: Catalog and pricing | Frontend | Exit gate | buyers search the catalog and see prices from the pricing API for their segment | 2026-11-23 | 2026-12-04 | Not started
BE-061 | Phase 4 / F4: Sourcing | Backend | Task | RFQ create, submit and distribute to matched manufacturers (rules-based scoring endpoint) | 2026-12-07 | 2026-12-18 | Not started
BE-062 | Phase 4 / F4: Sourcing | Backend | Task | Manufacturer quotes, buyer quote comparison, customer quotation with margins applied | 2026-12-07 | 2026-12-18 | Not started
BE-063 | Phase 4 / F4: Sourcing | Backend | Task | Sales qualification and QA threads | 2026-12-07 | 2026-12-18 | Not started
BE-064 | Phase 4 / F4: Sourcing | Backend | Task | Email at each hand-off | 2026-12-07 | 2026-12-18 | Not started
BE-065 | Phase 4 / F4: Sourcing | Backend | Hand-off | Write and freeze the Orders/payments contract | 2026-12-07 | 2026-12-16 | Not started
BE-066 | Phase 4 / F4: Sourcing | Backend | Exit gate | RFQ goes from draft to accepted quote end to end, with emails at each step | 2026-12-07 | 2026-12-18 | Not started
FE-067 | Phase 4 / F4: Sourcing | Frontend | Task | RFQ, Quote, AIMatching (rules-based scores), ManufacturerAssignedRFQs, ManufacturerQuoteSubmissions | 2026-12-07 | 2026-12-18 | Not started
FE-068 | Phase 4 / F4: Sourcing | Frontend | Task | BuyerQuoteComparison, CustomerQuotation, SalesQualification | 2026-12-07 | 2026-12-18 | Not started
FE-069 | Phase 4 / F4: Sourcing | Frontend | Task | BuyerQa, RaiseQaModal, AdminQaGovernance, AdminRfq and Quote monitors | 2026-12-07 | 2026-12-18 | Not started
FE-070 | Phase 4 / F4: Sourcing | Frontend | Hand-off | Review the Orders/payments contract | 2026-12-07 | 2026-12-16 | Not started
FE-071 | Phase 4 / F4: Sourcing | Frontend | Exit gate | RFQ to accepted quote passes the Playwright flow on staging | 2026-12-07 | 2026-12-18 | Not started
BE-072 | Phase 5 / F5: Orders and payments | Backend | Task | Order module: master order from accepted quote, admin approval, sub-order split, production status, status history | 2026-12-21 | 2027-01-05 | Not started
BE-073 | Phase 5 / F5: Orders and payments | Backend | Task | Payment module: proforma invoice, advance payment (percentage or fixed), Razorpay order created server-side | 2026-12-21 | 2027-01-05 | Not started
BE-074 | Phase 5 / F5: Orders and payments | Backend | Task | Razorpay payment.captured webhook: raw-body signature check, idempotent by event ID, outbox event | 2026-12-21 | 2027-01-05 | Not started
BE-075 | Phase 5 / F5: Orders and payments | Backend | Task | Tax invoice PDF (pdfmake), partial payments, refunds, overdue check as a scheduled job | 2026-12-21 | 2027-01-05 | Not started
BE-076 | Phase 5 / F5: Orders and payments | Backend | Hand-off | Write and freeze the Logistics/notifications/dashboards contract | 2026-12-21 | 2026-12-30 | Not started
BE-077 | Phase 5 / F5: Orders and payments | Backend | Exit gate | accepted quote becomes a paid, split order in Razorpay test mode; ledger totals match | 2026-12-21 | 2027-01-05 | Not started
FE-078 | Phase 5 / F5: Orders and payments | Frontend | Task | Order, MasterOrderSplitting, ManufacturerSubOrder, ProductionExecution | 2026-12-21 | 2027-01-05 | Not started
FE-079 | Phase 5 / F5: Orders and payments | Frontend | Task | BuyerOrderTracking, AdminOrderMonitor, ManufacturerOrderHistory | 2026-12-21 | 2027-01-05 | Not started
FE-080 | Phase 5 / F5: Orders and payments | Frontend | Task | Invoice (PDF download), BuyerAdvancePayments, Accounts | 2026-12-21 | 2027-01-05 | Not started
FE-081 | Phase 5 / F5: Orders and payments | Frontend | Task | razorpayService only opens Checkout with the API's order ID; payment status read from the API | 2026-12-21 | 2027-01-05 | Not started
FE-082 | Phase 5 / F5: Orders and payments | Frontend | Hand-off | Review the Logistics/notifications/dashboards contract | 2026-12-21 | 2026-12-30 | Not started
FE-083 | Phase 5 / F5: Orders and payments | Frontend | Exit gate | Razorpay test payment updates order status through the backend webhook | 2026-12-21 | 2027-01-05 | Not started
BE-084 | Phase 6 / F6: Logistics, notifications, dashboards | Backend | Task | Logistics module: shipment per sub-order with carrier and tracking number, status updates, delivery closes sub-order | 2027-01-06 | 2027-01-12 | Not started
BE-085 | Phase 6 / F6: Logistics, notifications, dashboards | Backend | Task | In-app notifications per user, streamed over Server-Sent Events, read/unread | 2027-01-06 | 2027-01-12 | Not started
BE-086 | Phase 6 / F6: Logistics, notifications, dashboards | Backend | Task | Dashboard module: one summary endpoint per role, CSV export of orders and invoices | 2027-01-06 | 2027-01-12 | Not started
BE-087 | Phase 6 / F6: Logistics, notifications, dashboards | Backend | Exit gate | sub-order ships, status reaches buyer screen without reload, delivery closes it | 2027-01-06 | 2027-01-12 | Not started
FE-088 | Phase 6 / F6: Logistics, notifications, dashboards | Frontend | Task | Shipment screen: carrier, tracking number, status updates, delivery confirmation | 2027-01-06 | 2027-01-12 | Not started
FE-089 | Phase 6 / F6: Logistics, notifications, dashboards | Frontend | Task | Notifications bell and list over Server-Sent Events, read/unread | 2027-01-06 | 2027-01-12 | Not started
FE-090 | Phase 6 / F6: Logistics, notifications, dashboards | Frontend | Task | Dashboards per role and ManufacturerDashboard on the summary API; CSV export buttons | 2027-01-06 | 2027-01-12 | Not started
FE-091 | Phase 6 / F6: Logistics, notifications, dashboards | Frontend | Task | Hide or mark Coming soon: FactoryBuddyCommunicationDesk, IntegrationsSettings, advanced Analytics and Reports | 2027-01-06 | 2027-01-12 | Not started
FE-092 | Phase 6 / F6: Logistics, notifications, dashboards | Frontend | Exit gate | shipment status change shows on buyer screen without reload; dashboards show live numbers | 2027-01-06 | 2027-01-12 | Not started
BE-093 | Hardening and code freeze | Backend | Task | Security pass: OWASP ASVS level 2 checklist on auth, uploads, payments; pnpm audit clean | 2027-01-12 | 2027-01-14 | Not started
BE-094 | Hardening and code freeze | Backend | Task | k6 smoke test on login, catalog search, RFQ and payment paths | 2027-01-12 | 2027-01-14 | Not started
BE-095 | Hardening and code freeze | Backend | Task | Production environment, secrets in a secret manager, Razorpay live keys loaded but off | 2027-01-12 | 2027-01-14 | Not started
BE-096 | Hardening and code freeze | Backend | Task | Daily database backup and one restore drill | 2027-01-12 | 2027-01-14 | Not started
BE-097 | Hardening and code freeze | Backend | Task | Seed data and beta tester accounts | 2027-01-12 | 2027-01-14 | Not started
BE-098 | Hardening and code freeze | Backend | Task | Code freeze (end of day) | 2027-01-12 | 2027-01-14 | Not started
FE-099 | Hardening and code freeze | Frontend | Task | Delete mockData.ts and the data parts of AppContext | 2027-01-12 | 2027-01-14 | Not started
FE-100 | Hardening and code freeze | Frontend | Task | Full Playwright regression of all exit-gate flows against staging | 2027-01-12 | 2027-01-14 | Not started
FE-101 | Hardening and code freeze | Frontend | Task | Check Chrome, Edge, Safari and phone-width layout on main buyer and manufacturer screens | 2027-01-12 | 2027-01-14 | Not started
FE-102 | Hardening and code freeze | Frontend | Task | Route-level code splitting; Sentry error tracking on | 2027-01-12 | 2027-01-14 | Not started
FE-103 | Hardening and code freeze | Frontend | Task | Production Vercel environment pointing at the production API | 2027-01-12 | 2027-01-14 | Not started
FE-104 | Hardening and code freeze | Frontend | Task | Code freeze (end of day) | 2027-01-12 | 2027-01-14 | Not started
BE-105 | Beta testing and launch | Backend | Task | Seed catalog, categories, price lists and pilot accounts | 2027-01-15 | 2027-01-14 | Not started
BE-106 | Beta testing and launch | Backend | Task | Watch error logs and the BullMQ failed-job queue every morning | 2027-01-15 | 2027-01-30 | Not started
BE-107 | Beta testing and launch | Backend | Task | Reproduce each backend bug as a failing test before fixing it | 2027-01-15 | 2027-01-30 | Not started
BE-108 | Beta testing and launch | Backend | Task | Run a Razorpay test payment and refund end to end every beta day | 2027-01-15 | 2027-01-30 | Not started
BE-109 | Beta testing and launch | Backend | Task | Before go-live: switch to Razorpay live keys, clear test data, take a backup | 2027-01-15 | 2027-01-28 | Not started
BE-110 | Beta testing and launch | Backend | Task | Handover pack: OpenAPI specs, env and secrets list, deploy/rollback runbook, backup/restore runbook, provider accounts, known issues | 2027-01-15 | 2027-01-30 | Not started
FE-111 | Beta testing and launch | Frontend | Task | Tester guide per role and in-app Report a problem link | 2027-01-15 | 2027-01-14 | Not started
FE-112 | Beta testing and launch | Frontend | Task | Triage each bug report (frontend, backend or contract) and tag the owner the same morning | 2027-01-15 | 2027-01-30 | Not started
FE-113 | Beta testing and launch | Frontend | Task | Watch Sentry errors every morning | 2027-01-15 | 2027-01-30 | Not started
FE-114 | Beta testing and launch | Frontend | Task | Rerun the Playwright regression on every beta deploy | 2027-01-15 | 2027-01-30 | Not started
FE-115 | Beta testing and launch | Frontend | Task | Before go-live: Vercel production on production API, no mock switch on, bundle checked for secrets | 2027-01-15 | 2027-01-28 | Not started
FE-116 | Beta testing and launch | Frontend | Task | Handover pack: build/deploy steps, env variables, screen-to-API map, Playwright guide, known issues | 2027-01-15 | 2027-01-30 | Not started

## Hand-offs
Phase | Contract frozen (mocks start) | Live on staging | Integration day | Days of mock-only build | Contract status | Staging status | Integration status
1 Identity | 2026-10-14 | 2026-10-28 | 2026-10-30 | 14 | Not started | Not started | Not started
2 Partners, files, compliance | 2026-10-28 | 2026-11-18 | 2026-11-20 | 21 | Not started | Not started | Not started
3 Catalog and pricing | 2026-11-18 | 2026-12-02 | 2026-12-04 | 14 | Not started | Not started | Not started
4 Sourcing (RFQ to quote) | 2026-12-02 | 2026-12-16 | 2026-12-18 | 14 | Not started | Not started | Not started
5 Orders and payments | 2026-12-16 | 2027-01-04 | 2027-01-05 | 19 | Not started | Not started | Not started
6 Logistics, notifications, dashboards | 2026-12-30 | 2027-01-11 | 2027-01-12 | 12 | Not started | Not started | Not started
Rules: backend writes contracts/<module>.yaml; frontend reviews within 1 working day; frozen when both approve. Breaking change after freeze needs both sign-offs. Integration day = frontend switches the phase from mock to staging and both run the exit-gate flow.

## Beta & launch
Date | Milestone | Owner
2027-01-14 | Code freeze (end of day) | Both
2027-01-15 | Beta opens: pilot accounts get invites | Both
2027-01-15 | Round 1 starts: testers run the full flow; daily triage at 10:00; fixes deploy daily (to 21 Jan) | Both
2027-01-22 | Round 2 build: all P0 and P1 bugs from round 1 fixed | Both
2027-01-25 | Release candidate; only P0 fixes after this | Both
2027-01-26 | Republic Day, off | -
2027-01-27 | Go/no-go with the product owner | Both
2027-01-28 | Production go-live: Razorpay live keys on, test data cleared | Both
2027-01-29 | Hypercare: watch logs and fix live issues | Both
2027-01-30 | Final delivery: handover and sign-off | Both
Bug severity
Severity | Meaning | Fix by
P0 | Flow blocked, wrong money, data leak, security hole | Same day
P1 | Major feature broken, no workaround | Within 2 working days
P2 | Works with a workaround, visual issues | Before go-live if time allows
P3 | Cosmetic or wish list | Post-launch backlog

## Scope
Area | In beta (30 Jan 2027) | After launch (Feb-Apr 2027)
Identity | IAM ported to Node.js, 8 roles, invites, TOTP 2FA, password reset, email verification | Per-device sessions for mobile
Partners and compliance | Onboarding wizard, profiles, document uploads, GST/PAN check via one provider, manual admin approval, audit log | AI document review, MCA checks, virus scan upgrade
Catalog and pricing | Products, 3-level categories, brands, attributes, UoM, tax, CSV import, price lists, margin rules, platform fees | Provider data feeds
Sourcing | RFQ to accepted quote, rules-based manufacturer matching, quote comparison, customer quotation, QA threads | AI matching model
Orders and payments | Master order, admin approval, sub-order split, production status, proforma and tax invoices (PDF), Razorpay advance and invoice payments, refunds | Daily reconciliation dashboard
Logistics | Shipment created by hand with carrier name and tracking number, status updates, delivery confirmation | Blue Dart and Delhivery APIs, temperature logs
Notifications | Email at each hand-off, in-app notifications over Server-Sent Events | SMS, WhatsApp, push, Factory Buddy conversations
Reporting | One summary dashboard per role, CSV export of orders and invoices | reporting-service, read models, PDF exports
Platform | One NestJS app with module boundaries, BullMQ jobs, staging and production | Kong gateway, RabbitMQ, split into services
Mobile | None | Buyer and Partner apps (master plan M0-M3)

## Risks
Track | Risk | Effect | Mitigation
Backend | One backend developer is a single point of failure | Any sick week slips beta | Contract-first specs and tests document the work; Phase 6 and dashboards are first to trim
Both | Phase 5 lands over Christmas and New Year | Orders and payments run late | Contract frozen 16 Dec so frontend builds on mocks before the break; refunds and overdue jobs last
Backend | Razorpay live KYC, GST provider and email provider take weeks | Go-live blocked on paperwork | Apply in Phase 0; build against sandboxes and fakes
Backend | IAM port changes behaviour | Existing users cannot log in | Same schema and shapes first; Java tests are the acceptance suite
Both | Late contract changes | Frontend rework | Freeze dates; breaking changes need both developers' sign-off
Backend | Money maths with JavaScript floats | Wrong invoice totals | Integer paise, decimal.js, rounding tests
Frontend | 72 screens for one developer | F2 and F5 run long | Split big modules only while touching them; hide out-of-scope screens
Frontend | AppContext (5,507 lines) and mockData.ts (7,132 lines) are tangled | Removing one slice breaks other screens | One domain per phase; delete its slice only after its Playwright flow passes
Frontend | Mocks drift from the real API | Surprises on integration day | Generate MSW handlers from the frozen spec, never by hand
Frontend | Backend slips a staging date | Frontend cannot finish its exit gate | Keep building the next phase on mocks; integrate when staging is up
Frontend | Secrets in the browser bundle today | Razorpay secret exposed | Removed on day 1 of F0

## Open questions
Owner | Question | Status | Decision
Product owner | Confirm the beta scope cuts on the Scope sheet | Open
Product owner | How many pilot buyers and manufacturers, and who recruits them by 8 Jan | Open
Backend | Hosting for the API: managed containers (AWS ECS, Render) or a VM | Open
Backend | Email provider and GST/PAN verification provider | Open
Product owner | Is a third developer or QA available in December if Phase 4 or 5 slips | Open
Frontend | Which out-of-scope screens are hidden and which show Coming soon | Open
Frontend | Bug tracker for beta testers (GitHub Issues, Jira or a form) | Open
Frontend | Browsers and minimum screen width to support at launch | Open